## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
1 | 1 |  | Choose the data file with at least 2 crypto currencies (either web scrape the csv file or download to use as csv) | MUST HAVE |  | Janavarshini PA | 3- Completed
1 | 1 |  | Store the data in the database. | MUST HAVE |  | Janavarshini PA | 3- Completed
1 | 1 |  | Calculate the metrics for the data and store in the data frame. | SHOULD HAVE |  | Janavarshini PA | 3- Completed
1 | 1 |  | Apply parallel tasks concepts to the above steps. | MUST HAVE |  | Janavarshini PA | 3- Completed
2 | 2 |  | Assign portfolio weights, verify rule compliance, then calculate portfolio return and risk. | MUST HAVE | 1 | Janavarshini PA | 3- Completed
2 | 2 |  | Create portfolio and portfolio_assets tables to store currencies, weights, returns, risk, and metrics, then store and fetch the data. | SHOULD HAVE | 1 | Janavarshini PA | 3- Completed
2 | 2 |  | Run multiple rule tests ( atleast 2 ) in parallel using ThreadPool and save outputs into the DB. | MUST HAVE | 1 | Janavarshini PA | 3- Completed
2 | 2 |  | Compare portfolio return with single asset return using sample data, plot graphs, derive insights, and export results to CSV. | SHOULD HAVE | 1 | Janavarshini PA | 3- Completed
2 | 2 |  | Prepare a .md file which should contain the milestone 2 work that is so far done. |  | 2 | Janavarshini PA | 3- Completed
3 | 3 |  | Implement 6 risk-identification rule,store results in the database,and send an email alert if any rule fails. | MUST HAVE | 2 | Janavarshini PA | 3- Completed
3 | 3 |  | Predict both portfolio and individual returns using linear regression model. | COULD HAVE | 2 | Janavarshini PA | 3- Completed
4 | 4 |  | Implement rule setter and calculate portfolio returns, store in db and apply stress test to see how portfolio returns behave | MUST HAVE | 3 | Janavarshini PA | 3- Completed

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 31 | 1 | 1 | 2 | 3 | 3 | 4 | 3 | 2 | 1 | 4 | 3 | 4 | 0 | 0
SPRINT 1 BACKLOG
1 | 1 | Choose the data file with at least 2 crypto currencies (either web scrape the csv file or download to use as csv) | 27.08.2025 | 27.08.2025 | Janavarshini PA | Design | 3- Completed | 1 | bar: Day 1
1 | 2 | Store the data in the database. | 27.08.2025 | 27.08.2025 | Janavarshini PA | Coding | 3- Completed | 1 | bar: Day 2
1 | 3 | Calculate the metrics for the data and store in the data frame. | 28.08.2025 | 28.08.2025 | Janavarshini PA | Coding | 3- Completed | 2 | Day 3: 2
1 | 4 | Apply parallel tasks concepts to the above steps. | 28.08.2025 | 29.08.2025 | Janavarshini PA | Coding | 3- Completed | 3 | Day 4: 3
2 | 5 | Assign portfolio weights, verify rule compliance, then calculate portfolio return and risk. | 02.09.2025 | 03.09.2025 | Janavarshini PA | Integration Test | 3- Completed | 3 | Day 5: 3
2 | 6 | Create portfolio and portfolio_assets tables to store currencies, weights, returns, risk, and metrics, then store and fetch the data. | 03.09.2025 | 04.09.2025 | Janavarshini PA | Coding | 3- Completed | 4 | Day 6: 4
2 | 7 | Run multiple rule tests ( atleast 2 ) in parallel using ThreadPool and save outputs into the DB. | 04.09.2025 | 06.09.2025 | Janavarshini PA | Integration Test | 3- Completed | 3 | Day 7: 3
2 | 8 | Compare portfolio return with single asset return using sample data, plot graphs, derive insights, and export results to CSV. | 08.09.2025 | 08.09.2025 | Janavarshini PA | System Test | 3- Completed | 2 | Day 8: 2
2 | 9 | Prepare a .md file which should contain the milestone 2 work that is so far done. | 09.09.2025 | 09.09.2025 | Janavarshini PA | Others | 3- Completed | 1 | bar: Day 9
3 | 10 | Implement 6 risk-identification rule,store results in the database,and send an email alert if any rule fails. | 16.09.2025 | 17.09.2025 | Janavarshini PA | System Test | 3- Completed | 4 | Day 10: 4
3 | 11 | Predict both portfolio and individual returns using linear regression model. | 18.09.2025 | 18.09.2025 | Janavarshini PA | Regression Test | 3- Completed | 3 | Day 11: 3
4 | 12 | Implement rule setter and calculate portfolio returns, store in db and apply stress test to see how portfolio returns behave. | 01.10.2025 | 02.10.2025 | Janavarshini PA | Unit Test | 3- Completed | 4 | Day 12: 4

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
M1 | 2025-08-27 | Select data source with at least 2 crypto assets (e.g., BTC, ETH) and decide between scraping or CSV download | Collected and validated crypto data from kaggle; created automated code to fetch and save as CSV
| 2025-08-28 | Store fetched data in a database | Built SQL table schema and inserted data using Python DB API
| 2025-08-29 | Compute return, volatility, and other key metrics | Implemented metric calculation functions and verified sample outputs
| 2025-08-30 | Optimize steps using parallel execution | Integrated ThreadPoolExecutor to parallelize metric computation and DB storage
M2 | 2025-09-02 | Assign portfolio weights and verify rule compliance | Applied rule-based logic to assign weights dynamically; validated compliance and stored results
| 2025-09-03 | Store currencies, weights, returns, risk, and metrics | Created the 2 database tables; tested data insertion and retrieval
| 2025-09-04 | Run multiple rule tests in parallel | Developed multi-threaded rule tester and stored outputs into the database
| 2025-09-08 | Compare portfolio vs single asset returns and visualize results | Generated comparison plots, derived insights, and exported results as CSV
| 2025-09-09 | Summarize milestone 2 work | Created structured .md documentation summarizing all M2 deliverables
M3 | 2025-09-16 | Implement and validate 6 portfolio risk-identification rules | Applied and tested all 6 rules; stored rule outcomes in DB
| 2025-09-17 | Automate alerts when a risk rule fails | Set up email alert service triggered upon rule failure
| 2025-09-18 | Predict returns using regression model | Trained linear regression models for portfolio and individual crypto returns
M4 | 2025-10-01 | Build rule setter and integrate with portfolio calculation | Developed flexible rule setter to define rules dynamically; computed returns and updated DB
| 2025-10-02 | Conduct stress test to analyze portfolio behavior | Designed stress scenarios (bull, bear, volatile), applied to model, and analyzed results

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | M1 | 2025-08-27 | 2025-08-30 | Janavarshini PA | Select crypto dataset (≥2 assets, e.g., BTC & ETH) and decide on data acquisition method; store data; compute metrics; optimize workflow | Manual data entry, sequential calculations, storing data without structure | Structured data collection, DB storage, metric calculation, parallel execution | Data fetched from Kaggle, saved as CSV; DB schema created; metrics computed; parallelized computation implemented
2 | M2 | 2025-09-02 | 2025-09-09 | Janavarshini PA | Assign portfolio weights, validate compliance, store portfolio and asset data, run parallel rule tests, compare vs single asset, visualize and summarize | Handling tasks one by one, not validating rules, skipping automated checks | Automated weight assignment, DB storage, visualization, documentation | Portfolio weights assigned using rules; DB tables created; multi-threaded rule tests executed; portfolio vs asset plots generated; M2 documentation completed
3 | M3 | 2025-09-16 | 2025-09-18 | Janavarshini PA | Implement 6 risk-identification rules, automate alerts for violations, predict returns using regression | Ignoring risk alerts, performing manual checks only | Risk evaluation automation, ML-based prediction | Risk rules applied and stored in DB; alert service set up for failures; regression models trained for portfolio and asset returns
4 | M4 | 2025-10-01 | 2025-10-02 | Janavarshini PA | Develop dynamic rule setter, integrate with portfolio calculations, conduct stress tests | Skipping stress test analysis, delaying integration of rule setter with portfolio calculations. | Portfolio return computation, rule management | Flexible rule setter implemented; returns calculated and updated in DB; stress scenarios applied and analyzed