## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Janavarshini PA | 27.08.2025 | Choose the data file with at least 2 crypto currencies and store in db-I used irrelevant table names | 1 | Janavarshini PA | Maintainability | Changed the table names to common ones | 27.08.2025 | Closed | I do this mistake everywhere as I use some name for execution at the momemt-Now I am aware of it everytime I work.
2 | Janavarshini PA | 08.09.2025 | In visualizations,I dint add the graph for risk comparison | 2 | Janavarshini PA | User Interface | Added it and derived insights from it | 09.09.2025 | Closed | Understood when to visualize what.
3 | Janavarshini PA | 02.09.2025 | The choosen dataset was not good for my operations or calculations | 2 | Janavarshini PA | Logical | I found a perfect dataset with multiple coins | 02.09.2025 | Closed | It was hard finding the good dataset,but I'm now aware of how to choose datasets based on the specific tasks.
4 | Janavarshini PA | 24.09.2025 | Was adviced to add regularization techniques to avoid overfitting | 3 | Janavarshini PA | Standards | The task was done | 25.09.2025 | Closed | Made me understand the importance of producing a clean work.
5 | Janavarshini PA | 01.10.2025 | Was adviced allocate weights dynamically to the coins | 4 | Janavarshini PA | Logical | The task was done | 02.010.2025 | Closed | I understood the use of doing it.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others